## README
Task Buddy - Delivery Blueprint Workbook
AI-powered to-do app for React Native + Expo. Generated with the /delivery-blueprint workflow. Project key: TB.
At a glance (live formulas)
Stories in backlog | 67
Total story points | 279
MVP points (Phase = MVP) | 58
Planned sprints | 10
Sprint capacity (points/sprint) - input | 30
Sprint 1 start date - input | 2026-11-02
Legends
Status flow | Draft > Ready > In Progress > Blocked > Code Review > QA Testing > UAT > Done
Priority | P0 critical path (Highest) ¦ P1 high ¦ P2 medium ¦ P3 nice-to-have (Low)
Points | Fibonacci (1,2,3,5,8). Stories above 8 must be split.
Waves | Sequence bands derived from the dependency-ordered sprint plan; workstreams run in parallel inside a wave.
Branch | <type>/tb-<ticket>/<short-kebab-title> e.g. feat/tb-015/quick-add-preview
Commit | Conventional Commits: feat(capture): add parse preview (TB-015)
Blue text | Input cell you can change (capacity, start date); totals recalculate.
Waves
Wave 1 - Foundations & Identity | Repo, tooling, design system, local data layer, Supabase, sign-in
Wave 2 - Task Core + AI Gateway & Guardrails | Task CRUD/screens plus the AI gateway with rate limits, quotas, output contracts and injection hardening
Wave 3 - Core AI Value | Natural-language capture, task breakdown, smart daily plan, beta distribution
Wave 4 - Retain & Engage | Notifications, buddy check-ins, sync, recurring tasks, procrastination helper, onboarding, compliance
Wave 5 - Channels & Intelligence | Buddy chat, voice, photo, weekly review, accessibility, v1.0 store release
Wave 6 - Platform & Ecosystem | Shared Spaces (multiplayer AI), billing, calendar, widgets, on-device AI
Workstreams
WS-A | Mobile App (UI & UX)
WS-B | Data, Auth & Sync
WS-C | AI & Backend (Edge Functions)
WS-D | Platform, DevOps & Release
WS-E | Quality & Accessibility
Tabs
Project Overview
Product Roadmap
Epic Backlog
Feature Backlog
Product Backlog
Sprint Backlog
Technical Backlog
Architecture & Decisions
Data Model
API Contracts
QA & Testing
DevOps & Deploy
Risk Register
Future Improvements
PM Import
Agile & AI Practices
Gaps & Assumptions

## Project Overview
Item | Detail
Product | Task Buddy - an AI to-do app that turns sentences, voice and photos into organized, scheduled tasks and nudges you to finish them.
Summary | Local-first React Native (Expo) app. A server-side AI gateway handles capture parsing, task breakdown, daily planning, check-ins, chat and weekly review. Later phases add voice/photo, Shared Spaces where people and an AI agent collaborate, billing, calendar, widgets and optional on-device AI.
Objectives | 1) MVP in about 2 weeks: sign in, tasks, natural-language capture, AI breakdown. 2) v1.0 store release by Sprint 7 with plan, reminders, check-ins, voice/photo, weekly review, compliance. 3) Shared Spaces (multiplayer AI) and Pro tier in Phase 3.
Target users | Busy individuals who capture tasks in messy language (English/Taglish), students and young professionals, and later small teams/families sharing a space.
KPI (proposed targets) | Activation: first AI-created task within 24h of signup >= 60% AI parse accuracy on golden set >= 90% AI p95 latency < 6 s (parse/breakdown) Crash-free sessions >= 99.5% D7 retention >= 25% AI cost per active user per month under a budget set after 4 weeks of ledger data
Constraints | Solo developer with AI coding agents; 30 pts/sprint; LLM key server-side only; works offline for core task use; store policy compliance (account deletion, AI disclosure).
Assumptions | See 'Gaps & Assumptions' tab.
Top risks | See 'Risk Register' tab: AI cost, prompt injection, sync data loss, store rejection, solo capacity.
Stack (locked) | Expo + RN + TypeScript, Expo Router, NativeWind, Zustand + TanStack Query, RHF + Zod, expo-sqlite + Drizzle, Supabase (Auth/Postgres/Realtime/Storage/Edge Functions), Claude via gateway, expo-notifications, expo-speech-recognition, RevenueCat, Sentry, PostHog, Jest + RNTL + Maestro, GitHub Actions + EAS.

## Product Roadmap
Phase | Sprints | Start | End | Goal | Key outcomes | Points | Priority focus | Dependencies | Release target
MVP | Sprint 1-2 | 2026-11-02 | 2026-11-13 | Capture and breakdown on a solid base | Sign in, tasks, quick-add, AI breakdown, AI gateway with guardrails | 60 | P0/P1 | See Epic Backlog | Internal MVP
Phase 2a - Beta | Sprint 3-5 | 2026-11-16 | 2026-12-04 | Plan, retain and engage | Daily plan, undo, evals, TestFlight/Play beta, reminders, sync, lists, recurring, push, check-ins, onboarding, E2E | 84 | P0/P1 | See Epic Backlog | Private beta (Sprint 3 onward)
Phase 2b - v1.0 | Sprint 6-7 | 2026-12-07 | 2026-12-18 | Channels, intelligence and launch | Compliance, buddy chat, voice, photo, weekly review, accessibility, performance, analytics | 56 | P1/P2 | See Epic Backlog | v1.0 store release (end Sprint 7)
Phase 3 - Platform | Sprint 8-10 | 2026-12-21 | 2027-01-08 | Shared Spaces and monetization | Spaces, shared lists, shared AI agent with permissions and audit, billing, calendar, widgets, on-device AI | 79 | P1/P2 | See Epic Backlog | Spaces beta (Sprint 9), Pro tier (Sprint 10)

## Epic Backlog
Epic ID | Name | Description | Business Value | Priority | Waves | Dependencies | Acceptance Criteria | Stories | Points | Status
EP-01 | Foundations & DevOps | Repository, tooling, CI/CD, design system and navigation shell. | Every later story depends on a consistent, testable, shippable base. | P0 | 1 | - | Clean clone boots on iOS+Android; CI green on PR; dev-client build installs. | 4 | 11 | Draft
EP-02 | Auth & Accounts | Supabase backend baseline, email OTP and social sign-in, settings. | Identity is required for AI quotas, sync, push and shared spaces. | P0 | 1 | EP-01 | User can sign in/out; sessions persist; RLS blocks cross-user reads. | 4 | 10 | Draft
EP-03 | Task Core & Sync | Local-first task data, CRUD screens, lists/tags/search, recurring tasks, offline sync. | The app is a to-do list first; it must be fast, offline-capable and reliable. | P0 | 1-4 | EP-01 | Tasks work fully offline; sync converges across two devices with no data loss. | 8 | 37 | Draft
EP-04 | AI Gateway & Guardrails | Single Edge Function gateway to the LLM with auth, rate limits, quotas, output contracts, injection hardening, optional on-device inference. | Keeps API keys off devices, caps cost, and makes AI output safe and typed. | P0 | 2 | EP-02 | No AI call reaches the provider without auth, quota check and validated schema. | 5 | 21 | Draft
EP-05 | Natural-Language Capture | Type a sentence, get structured tasks with dates, priorities and lists. | Headline feature: capture friction drops to a single sentence. | P0 | 3 | EP-03, EP-04 | >=90% of golden-set sentences produce correct task count and due dates. | 3 | 10 | Draft
EP-06 | AI Task Breakdown | Break a vague task into subtasks with time estimates. | Turns overwhelming tasks into actionable steps; reduces procrastination. | P1 | 3 | EP-03, EP-04 | Breakdown returns 3-8 actionable subtasks the user can accept or regenerate. | 1 | 5 | Draft
EP-07 | Smart Daily Plan | Work-hours settings, AI daily schedule, plan UI and re-planning on missed tasks. | Daily habit loop: open app, see a realistic plan. | P1 | 3-4 | EP-03, EP-04 | Plan fits within available hours and respects due dates; re-plan after overdue. | 4 | 19 | Draft
EP-08 | Notifications & Buddy Check-ins | Local reminders, permission flow, push infrastructure, contextual AI check-ins with quick actions. | Retention engine; the 'buddy' personality lives here. | P1 | 4 | EP-03, EP-04 | Reminders fire on time offline; check-ins respect quiet hours and caps. | 4 | 16 | Draft
EP-09 | Procrastination Helper & Buddy Chat | Detect repeatedly postponed tasks, suggest starter steps, chat assistant with confirmed actions, personality settings. | Differentiator: the app helps you finish, not just list. | P1 | 4-5 | EP-04, EP-08 | Chat can propose add/complete/reschedule and only executes after user confirmation. | 4 | 17 | Draft
EP-10 | Voice & Photo Capture | Voice-to-tasks via on-device speech recognition and photo-to-tasks via vision, with media privacy controls. | Capture anywhere: hands-free and from handwritten lists. | P1 | 5 | EP-05 | Voice and photo feed the same review screen; raw media deleted within 24h. | 3 | 13 | Draft
EP-11 | Weekly Review & Insights | Weekly stats and AI-written review of wins, slips and patterns. | Reflection loop that builds long-term retention. | P2 | 5 | EP-03, EP-04 | Review generates in <15s from real stats and cites only real data. | 2 | 8 | Draft
EP-12 | Shared Spaces (Multiplayer AI) | Shared spaces with members, realtime shared lists, assignment, a shared AI agent with scoped permissions and audit log. | Strategic: humans and an AI agent collaborating in one shared space. | P2 | 6 | EP-03, EP-04, EP-08 | Two members see changes in <2s; agent actions are permissioned, confirmable and audited. | 9 | 47 | Draft
EP-13 | Monetization, Compliance & Release | Beta distribution, onboarding, privacy/compliance, store release, billing tiers, calendar, widgets. | Gets the app legally and commercially into users' hands. | P0 | 3-6 | EP-01, EP-02 | v1.0 passes store review; account deletion and data export work; Pro tier unlocks quotas. | 9 | 41 | Draft
EP-14 | Quality, Observability & Accessibility | Crash reporting, E2E tests, AI evals, analytics, accessibility, i18n, performance. | Keeps AI quality, stability and inclusivity measurable. | P1 | 3-5 | EP-01 | Crash-free sessions >=99.5%; AI eval suite gates CI; WCAG-aligned labels and dynamic type. | 7 | 24 | Draft

## Feature Backlog
Feature ID | Epic | Name | Description | Priority | Complexity | Dependencies | Status
FT-01 | EP-01 | Project scaffold & tooling | Expo + TS + Router, lint, typecheck, aliases. | P0 | S | - | Draft
FT-02 | EP-01 | CI/CD & build profiles | GitHub Actions, EAS profiles, dev client. | P0 | S | FT-01 | Draft
FT-03 | EP-01 | Design system & navigation shell | Tokens, primitives, tab/modal shell. | P0 | M | FT-01 | Draft
FT-06 | EP-02 | Supabase backend baseline | Projects, env, RLS baseline, types. | P0 | S | FT-01 | Draft
FT-04 | EP-02 | Email OTP sign-in | OTP auth with secure session storage. | P0 | S | FT-06 | Draft
FT-05 | EP-02 | Social sign-in | Apple and Google sign-in. | P2 | S | FT-04 | Draft
FT-49 | EP-02 | Settings & preferences | Settings screen shell and preference store. | P1 | S | FT-03 | Draft
FT-07 | EP-03 | Local data layer | SQLite + Drizzle schema, migrations, repositories. | P0 | M | FT-01 | Draft
FT-08 | EP-03 | Task management UI | CRUD, Today/Inbox, task detail. | P0 | M | FT-07 | Draft
FT-09 | EP-03 | Organization | Lists, tags, filters, full-text search. | P2 | M | FT-08 | Draft
FT-10 | EP-03 | Recurring tasks | RRULE-based repetition. | P2 | M | FT-08 | Draft
FT-11 | EP-03 | Offline-first sync | Push/pull sync with conflict handling. | P1 | L | FT-07, FT-04 | Draft
FT-12 | EP-04 | AI gateway | Edge Function proxy to the LLM provider. | P0 | M | FT-06, FT-04 | Draft
FT-13 | EP-04 | Usage guardrails | Rate limits and token quotas. | P0 | S | FT-12 | Draft
FT-14 | EP-04 | Output contracts & safety | JSON schemas, validation, injection hardening. | P0 | M | FT-12 | Draft
FT-42 | EP-04 | On-device inference (experimental) | Offline parsing with a small local model. | P3 | L | FT-14 | Draft
FT-15 | EP-05 | Quick-add parse | Typed capture with parse preview and parser. | P0 | M | FT-08, FT-14 | Draft
FT-16 | EP-05 | Review & undo | Edit-before-confirm and undo for AI tasks. | P1 | S | FT-15 | Draft
FT-17 | EP-06 | Breakdown | AI subtasks with estimates and review UI. | P1 | M | FT-08, FT-14 | Draft
FT-18 | EP-07 | Work hours | Availability and daily capacity settings. | P1 | S | FT-49 | Draft
FT-19 | EP-07 | Plan generation | AI scheduler for the day. | P1 | L | FT-14, FT-18 | Draft
FT-20 | EP-07 | Plan UI & re-plan | Plan view, reorder, re-plan on missed tasks. | P1 | M | FT-19 | Draft
FT-21 | EP-08 | Reminders | Local notifications and permission flow. | P1 | M | FT-08 | Draft
FT-22 | EP-08 | Push infrastructure | Expo push tokens and server sending. | P1 | M | FT-21 | Draft
FT-23 | EP-08 | Buddy check-ins | Contextual AI nudges with quick actions. | P1 | M | FT-22, FT-19 | Draft
FT-24 | EP-09 | Procrastination helper | Detect postponements, suggest starter steps. | P2 | M | FT-08, FT-14 | Draft
FT-25 | EP-09 | Buddy chat | Streaming chat with confirmed actions. | P1 | L | FT-14, FT-13 | Draft
FT-26 | EP-09 | Personality | Friendly/coach/chill and English/Taglish. | P3 | S | FT-25 | Draft
FT-27 | EP-10 | Voice capture | On-device speech recognition into the parser. | P1 | M | FT-15 | Draft
FT-28 | EP-10 | Photo capture | Vision extraction of tasks from photos. | P2 | M | FT-15 | Draft
FT-29 | EP-10 | Media privacy | Upload limits, auto-deletion, consent. | P1 | S | FT-27, FT-28 | Draft
FT-30 | EP-11 | Weekly stats | Completion and slip statistics. | P2 | S | FT-08 | Draft
FT-31 | EP-11 | AI weekly review | Narrative review and insights screen. | P2 | M | FT-30, FT-14 | Draft
FT-32 | EP-12 | Spaces & membership | Spaces, roles, invites, RLS. | P2 | L | FT-11 | Draft
FT-33 | EP-12 | Shared lists realtime | Realtime shared tasks, assignment, comments. | P2 | L | FT-32 | Draft
FT-34 | EP-12 | Shared AI agent | Group-context agent and task balancing. | P2 | L | FT-33, FT-35 | Draft
FT-35 | EP-12 | Agent permissions & audit | Scopes, confirmations, audit log. | P1 | M | FT-32, FT-12 | Draft
FT-36 | EP-13 | Subscription | Billing, tiers and tiered quotas. | P2 | L | FT-04, FT-13 | Draft
FT-37 | EP-13 | Compliance | Privacy docs, account deletion, data export. | P0 | M | FT-11 | Draft
FT-38 | EP-13 | Onboarding | First-run flow and permission priming. | P1 | M | FT-21, FT-49 | Draft
FT-39 | EP-13 | Beta & store release | TestFlight/Play testing, OTA, store submission. | P0 | M | FT-02 | Draft
FT-40 | EP-13 | Calendar integration | Read device calendar to inform plans. | P3 | M | FT-19 | Draft
FT-41 | EP-13 | Widgets | Home-screen Today widget. | P3 | M | FT-08 | Draft
FT-43 | EP-14 | Observability | Crash reporting and release health. | P1 | S | FT-02 | Draft
FT-44 | EP-14 | E2E testing | Maestro flows for critical paths. | P1 | M | FT-08 | Draft
FT-45 | EP-14 | AI evals | Golden sets and regression gate in CI. | P1 | M | FT-15 | Draft
FT-46 | EP-14 | Accessibility & i18n | Screen reader, dynamic type, Taglish/Filipino strings. | P1 | M | FT-08 | Draft
FT-47 | EP-14 | Analytics | Event taxonomy and funnels. | P2 | S | FT-03 | Draft
FT-48 | EP-14 | Performance | Startup and list performance budgets. | P2 | S | FT-08 | Draft

## Product Backlog
Story ID | Epic | Feature | Title | User Story | Acceptance Criteria (testable) | Priority | Points | Wave | Workstream | Sprint | Phase | Blocked By | Status
US-001 | EP-01 | FT-01 | Scaffold Expo app (TypeScript, Router, lint, aliases) | As a developer, I want a TypeScript Expo app scaffolded with Expo Router, strict TS, ESLint/Prettier and path aliases, so that every later story starts from one consistent base. | - Given a fresh clone, when I run `pnpm install && pnpm start`, then the app boots on an iOS simulator and an Android emulator with a placeholder home route - Given the repo, when I run `pnpm lint && pnpm typecheck`, then both pass with zero errors in strict mode - The folder structure matches CLAUDE.md section 3 and `docs/tickets/_TEMPLATE.md` exists | P0 | 3 | Wave 1 | WS-D | 1 | MVP | - | Ready
US-002 | EP-01 | FT-02 | CI pipeline and EAS build profiles | As a developer, I want CI and EAS build profiles, so that every PR is linted, typechecked, tested and installable as a dev client. | - Given a PR, when it is opened, then GitHub Actions runs lint, typecheck and unit tests and finishes in under 8 minutes - Given `eas build --profile development`, then a dev-client build is produced and installs on a device or simulator - Branch protection requires green CI and one review before merge to main | P0 | 3 | Wave 1 | WS-D | 1 | MVP | US-001 | Ready
US-003 | EP-01 | FT-03 | Design system: theme tokens and UI primitives | As a user, I want a consistent, accessible look in light and dark mode, so that the app feels polished and readable. | - Given the system theme changes, when the app is open, then all primitives (Button, Input, Card, Checkbox, Sheet) switch theme without a reload - Colour tokens meet 4.5:1 contrast for body text in both themes - Each primitive has a typed props interface and is used by at least one screen (reuse-first) | P0 | 3 | Wave 1 | WS-A | 1 | MVP | US-001 | Ready
US-004 | EP-01 | FT-03 | App shell: tab navigation and task modal | As a user, I want tab navigation (Today, Inbox, Buddy, Settings) and a task detail modal, so that I can move around the app quickly. | - Given the app is open, when I tap each tab, then the matching screen renders in under 300 ms - Given the deep link `taskbuddy://task/<id>`, when opened, then the task detail modal is shown - The Android back gesture and iOS swipe-back close the modal without losing state | P0 | 2 | Wave 1 | WS-A | 1 | MVP | US-003 | Ready
US-005 | EP-02 | FT-06 | Supabase projects, env config and RLS baseline | As a developer, I want Supabase dev/staging/prod projects with env config and RLS baseline, so that auth and data are secure from the first commit. | - Given three Supabase projects, then URLs and anon keys are injected through EAS env and no service-role key exists in the client bundle - Given users A and B, when A queries B's profile row, then RLS returns zero rows (automated test) - TypeScript types are generated from the schema in CI and the build fails on drift | P0 | 2 | Wave 1 | WS-B | 1 | MVP | US-001 | Ready
US-006 | EP-02 | FT-04 | Email OTP sign-in with secure session | As a user, I want to sign in with an emailed 6-digit code, so that I can use the app without remembering a password. | - Given a valid email and correct code, when I submit, then I land on Today within 3 seconds and the session survives an app restart - Given a wrong or expired code, then an inline error is shown and I can request a new code after 30 seconds - Sessions are stored in expo-secure-store and refresh automatically; sign-out clears them | P0 | 3 | Wave 1 | WS-B | 1 | MVP | US-005, US-004 | Ready
US-007 | EP-03 | FT-07 | Local SQLite schema, migrations and repositories | As a developer, I want a local SQLite schema with migrations and repositories, so that the app works offline and is ready for sync. | - Given a first launch, then migrations run and tables tasks, subtasks, lists, tags exist with id (UUIDv7), updated_at and deleted_at - Given a v1 database with data, when v2 migration runs in a test, then no rows are lost - Given 10,000 tasks, a list query returns in under 50 ms at p95 on a mid-range Android device | P0 | 3 | Wave 1 | WS-B | 1 | MVP | US-001 | Ready
US-008 | EP-04 | FT-12 | AI gateway Edge Function with JWT auth | As a developer, I want a Supabase Edge Function AI gateway that verifies the user JWT and calls the LLM through a provider interface, so that API keys never ship in the app. | - Given an unauthenticated request, then the gateway returns 401 and never calls the provider - Given a valid request, then routes /parse, /breakdown, /plan use their configured model and a 20-second timeout - The provider API key exists only as an Edge Function secret and a search of the app bundle finds no key | P0 | 5 | Wave 2 | WS-C | 1 | MVP | US-005, US-006 | Ready
US-009 | EP-04 | FT-13 | Per-user AI rate limits and token quotas | As the product owner, I want per-user rate limits and daily token quotas on every AI call, so that cost and abuse are capped from day one. | - Given a free user, when they make a 31st AI call within an hour, then the gateway returns 429 with Retry-After and the app shows a friendly message - Every AI call writes a row to the usage ledger with user, route, model, input/output tokens and cost estimate - A daily token quota per user is enforced and the quota resets at 00:00 UTC | P0 | 3 | Wave 2 | WS-C | 1 | MVP | US-008 | Ready
US-010 | EP-04 | FT-14 | AI output schemas, validation and repair retry | As a developer, I want JSON schemas and validation for every AI response, so that malformed model output never reaches the database. | - Given 200 golden inputs, then at least 98% of responses validate against the schema after at most one automatic repair retry - Given invalid output after the retry, then the gateway returns the typed error AI_BAD_OUTPUT and nothing is persisted - Prompt templates are versioned in the repo and the version is logged with each request | P0 | 3 | Wave 2 | WS-C | 1 | MVP | US-008 | Ready
US-011 | EP-04 | FT-14 | Prompt-injection and input hardening | As the product owner, I want input hardening against prompt injection, so that user text can never exfiltrate prompts or trigger actions. | - Given a corpus of 20 injection prompts (e.g. 'ignore previous instructions'), then none returns the system prompt or triggers a tool action - Inputs over 2,000 characters are rejected with 413 and control characters are stripped - AI-proposed actions are never executed server-side; the client must confirm | P0 | 2 | Wave 2 | WS-C | 2 | MVP | US-008 | Ready
US-012 | EP-03 | FT-08 | Task CRUD with due date and priority | As a user, I want to create, edit, complete and delete tasks with a due date and priority, so that I can manage my work. | - Given the add-task form, when I save a title with due date and priority, then the task appears in the right list instantly (optimistic) and persists after restart - Given a task, when I complete it, then it moves to Completed with a timestamp and can be un-completed - Deleting a task is a soft delete (deleted_at) with a 5-second undo | P0 | 5 | Wave 2 | WS-A | 2 | MVP | US-007, US-004 | Ready
US-013 | EP-03 | FT-08 | Today and Inbox screens with swipe actions | As a user, I want Today and Inbox screens grouped by due state with swipe actions, so that I see what matters now. | - Given tasks due today, overdue and undated, then Today shows Overdue, Today and Later groups and Inbox shows undated tasks - Given a task row, when I swipe right/left, then it completes or reschedules to tomorrow - Empty states explain the next action; a list of 500 tasks scrolls at 60 fps in a release build | P0 | 5 | Wave 2 | WS-A | 2 | MVP | US-012 | Ready
US-014 | EP-03 | FT-08 | Task detail screen with notes and subtasks | As a user, I want a task detail screen with notes, subtasks and due/priority controls, so that I can capture context. | - Given a task, when I open it, then I can edit title, notes, due date, priority and manage a subtask checklist - Given all subtasks are checked, then I am offered to complete the parent task - Edits autosave within 500 ms of the last keystroke | P0 | 3 | Wave 2 | WS-A | 2 | MVP | US-012 | Ready
US-015 | EP-05 | FT-15 | Quick-add with AI parse preview | As a user, I want to type a sentence like 'call landlord tomorrow 9am, buy rice and eggs' and see the parsed tasks before saving, so that capture takes seconds. | - Given a sentence with three tasks, then the preview lists three tasks with parsed due dates and priorities within 3 seconds (p95) - Given the device is offline, then the quick-add falls back to saving one plain task and shows 'AI unavailable' - Saving the preview creates the tasks in one transaction | P0 | 5 | Wave 3 | WS-A | 2 | MVP | US-012, US-010, US-009 | Ready
US-016 | EP-05 | FT-15 | Natural-language parser: dates, priority, timezone | As a user, I want relative dates and priorities understood in my timezone, so that 'Friday' and 'urgent' mean what I expect. | - Given the golden set of 100 English/Taglish sentences, then at least 90% produce the correct task count and due date in the user's timezone - Given an ambiguous date, then confidence is below 0.6 and the preview highlights the field for review - Prompts include current date/time and timezone and never include other users' data | P0 | 3 | Wave 3 | WS-C | 2 | MVP | US-010, US-011 | Ready
US-017 | EP-06 | FT-17 | AI task breakdown into subtasks with estimates | As a user, I want to tap 'Break it down' on a vague task and review suggested subtasks with time estimates, so that big tasks become doable. | - Given a task titled 'Launch my website', when I tap Break it down, then 3-8 subtasks with minute estimates appear within 6 seconds (p95) - Given the suggestions, then I can accept all, accept some, edit, or regenerate - Accepting adds subtasks to the task and totals the estimate on the parent | P1 | 5 | Wave 3 | WS-A | 2 | MVP | US-014, US-010, US-009 | Ready
US-018 | EP-02 | FT-49 | Settings screen shell and preference registry | As a user, I want a Settings screen, so that I can manage my account and preferences in one place. | - Given the Settings tab, then I can see my account email, sign out, and open preference sections - Preference changes persist locally and apply immediately - Settings sections are driven by a registry so later stories add rows without editing the screen | P1 | 2 | Wave 3 | WS-A | 2 | Phase 2 | US-004 | Ready
US-019 | EP-07 | FT-18 | Work hours and daily capacity settings | As a user, I want to set my working hours and daily capacity, so that plans fit my real day. | - Given work hours 9:00-17:00 and capacity 5 hours, then the value persists and is exposed to the planner - Invalid ranges (end before start) are blocked with an inline error - Default values are applied for users who skip the setting | P1 | 3 | Wave 3 | WS-A | 3 | Phase 2 | US-018 | Draft
US-020 | EP-07 | FT-19 | AI daily plan generation | As a user, I want an AI-generated plan for today, so that I know what to do and when. | - Given tasks with estimates and due dates, then the plan schedules blocks inside my work hours and never exceeds daily capacity - Given a task due today, then it is scheduled before tasks with later due dates - Tasks that do not fit are returned as unscheduled with a reason | P1 | 8 | Wave 3 | WS-C | 3 | Phase 2 | US-010, US-019, US-012, US-009 | Draft
US-021 | EP-07 | FT-20 | Daily plan view with reorder and accept | As a user, I want to see, reorder and accept my daily plan on the Today screen, so that I stay in control. | - Given a generated plan, then Today shows time blocks and I can drag to reorder or remove a block - Given I accept the plan, then it is saved and shown on next open without another AI call - Pull-to-refresh regenerates the plan and counts against my quota | P1 | 5 | Wave 3 | WS-A | 3 | Phase 2 | US-020, US-013 | Draft
US-022 | EP-05 | FT-16 | Edit and undo AI-created tasks | As a user, I want to edit AI-created tasks and undo them, so that mistakes are cheap. | - Given AI-created tasks, when I tap Undo within 10 seconds, then all of them are removed - Given a parsed task in preview, then every field is editable before save - AI-created tasks carry a source flag for analytics and evals | P1 | 2 | Wave 3 | WS-A | 3 | Phase 2 | US-015 | Draft
US-023 | EP-14 | FT-43 | Crash reporting with Sentry and source maps | As a developer, I want crash and error reporting with source maps, so that I find problems before users do. | - Given a forced JS error and a forced native crash in a preview build, then both appear in Sentry with readable stack traces - PII (task titles, notes) is scrubbed from breadcrumbs and events - Release health shows crash-free sessions per build | P1 | 2 | Wave 3 | WS-D | 3 | Phase 2 | US-001, US-002 | Draft
US-024 | EP-13 | FT-39 | TestFlight and Play beta builds with OTA updates | As a tester, I want TestFlight and Play internal builds with OTA updates, so that I can use the app daily and give feedback. | - Given a merge to main, then a preview build is uploaded to TestFlight and Play internal testing - Given a JS-only change, then EAS Update delivers it to the preview channel without a store build - A feedback link is reachable from Settings | P1 | 3 | Wave 3 | WS-D | 3 | Phase 2 | US-002, US-023, US-013 | Draft
US-025 | EP-14 | FT-45 | AI eval harness with golden sets and CI gate | As a developer, I want golden sets and an eval runner for parse, breakdown and plan, so that prompt or model changes cannot silently regress quality. | - Given golden sets (100 parse, 30 breakdown, 30 plan cases), then `pnpm eval` prints per-feature pass rates - CI fails when a pass rate drops more than 3 points from the stored baseline - Eval runs are rate-limited and cost-capped to a configured budget | P1 | 5 | Wave 3 | WS-E | 3 | Phase 2 | US-016, US-017, US-020 | Draft
US-026 | EP-08 | FT-21 | Local due-date reminders | As a user, I want reminders at a task's due time even offline, so that I do not miss things. | - Given a task with a due time, then a local notification fires within 60 seconds of that time with the app closed - Completing or deleting the task cancels its pending notification - Editing the due time reschedules the notification | P1 | 3 | Wave 4 | WS-A | 4 | Phase 2 | US-012 | Draft
US-027 | EP-08 | FT-21 | Notification permission flow and quiet hours | As a user, I want a clear notification permission flow with quiet hours, so that nudges are welcome, not annoying. | - Given first reminder use, then a priming screen explains why before the OS permission prompt appears - Given quiet hours 22:00-07:00, then no reminder or check-in is delivered in that window - If permission is denied, the Settings row links to OS settings | P1 | 3 | Wave 4 | WS-A | 4 | Phase 2 | US-018, US-026 | Draft
US-028 | EP-07 | FT-20 | Re-plan on missed or finished tasks | As a user, I want the plan to adapt when I miss or finish tasks early, so that my day stays realistic. | - Given overdue planned blocks, when I tap Re-plan, then remaining tasks are rescheduled into the rest of today or tomorrow - Re-plan preserves blocks I pinned - Re-plan costs one AI call and respects rate limits | P1 | 3 | Wave 4 | WS-C | 4 | Phase 2 | US-021 | Draft
US-029 | EP-03 | FT-11 | Offline-first sync across devices | As a user, I want my tasks synced across devices and backed up, so that I never lose data. | - Given two devices on one account, when I edit on device A, then device B shows the change within 10 seconds of being online - Given the same task edited offline on both devices, then the later updated_at wins and no task is duplicated or lost (automated test) - Soft-deleted tasks sync as tombstones and purge after 30 days | P1 | 8 | Wave 4 | WS-B | 4 | Phase 2 | US-007, US-006, US-012 | Draft
US-030 | EP-03 | FT-09 | Lists, tags and filters | As a user, I want lists and tags with filters, so that I can organize my tasks. | - Given lists and tags, then I can assign them to a task and filter Today/Inbox by list or tag - Deleting a list asks whether to move or delete its tasks - The parser can assign an existing list by name | P2 | 5 | Wave 4 | WS-A | 4 | Phase 2 | US-012 | Draft
US-031 | EP-03 | FT-10 | Recurring tasks (RRULE) | As a user, I want recurring tasks (daily, weekly, custom), so that routines are automatic. | - Given a weekly Monday/Thursday rule, then completing an instance creates the next occurrence on the correct date in my timezone - Editing 'this and future' vs 'only this' is supported - Recurrence uses RFC 5545 RRULE strings and passes 20 date-edge test cases (DST, month end) | P2 | 5 | Wave 4 | WS-A | 4 | Phase 2 | US-012 | Draft
US-032 | EP-08 | FT-22 | Push token registration and server sender | As a developer, I want push tokens and a server-side sender, so that check-ins reach users when the app is closed. | - Given a signed-in device, then its Expo push token is registered and removed on sign-out - Given a send request, then the Edge Function delivers via Expo Push and records receipts; invalid tokens are pruned - A per-user daily cap of 3 pushes is enforced server-side | P1 | 5 | Wave 4 | WS-C | 5 | Phase 2 | US-006, US-008, US-027 | Draft
US-033 | EP-08 | FT-23 | Buddy check-ins with quick-reply actions | As a user, I want occasional, useful buddy check-ins with quick replies, so that I stay on track without opening the app. | - Given unfinished planned tasks at 16:00 local, then I get a check-in naming them with actions Done / Move to tomorrow / Snooze - Tapping an action updates the task without opening the app - Check-in text is generated by the AI with a max of 160 characters and respects quiet hours | P1 | 5 | Wave 4 | WS-C | 5 | Phase 2 | US-032, US-020, US-009 | Draft
US-034 | EP-09 | FT-24 | Detect repeatedly postponed tasks | As a user, I want the buddy to notice tasks I keep postponing, so that I can get unstuck. | - Given a task postponed 3 times, then it is flagged and I am offered help on the task detail screen - Postpone count is stored locally and syncs - I can dismiss the flag and it does not return for 7 days | P2 | 3 | Wave 4 | WS-A | 5 | Phase 2 | US-014, US-026 | Draft
US-035 | EP-09 | FT-24 | AI 10-minute starter step | As a user, I want a tiny 10-minute starter step for a stuck task, so that starting feels easy. | - Given a flagged task, when I tap Help me start, then I can optionally say what is blocking me and receive one concrete step under 10 minutes - Accepting adds the step as the first subtask and schedules it today - The response is validated against the starter-step schema | P2 | 3 | Wave 4 | WS-C | 5 | Phase 2 | US-034, US-010, US-009 | Draft
US-036 | EP-02 | FT-05 | Sign in with Apple and Google | As a user, I want to sign in with Apple or Google, so that onboarding is one tap. | - Given Apple and Google accounts, then each signs in and links to the same user when the email matches - Sign in with Apple is offered wherever another social option exists (store requirement) - Cancelling the flow returns to sign-in with no error state | P2 | 3 | Wave 4 | WS-B | 5 | Phase 2 | US-006 | Draft
US-037 | EP-13 | FT-38 | Onboarding flow (hours, quiet hours, tone) | As a new user, I want a short onboarding that sets work hours and notification preferences, so that the app is useful on day one. | - Given a new account, then onboarding takes at most 4 screens and can be skipped - Onboarding writes work hours, quiet hours and buddy tone to settings - Completion is recorded so it is never shown again | P1 | 5 | Wave 4 | WS-A | 5 | Phase 2 | US-027, US-019, US-018 | Draft
US-038 | EP-14 | FT-44 | Maestro E2E flows for critical paths | As a developer, I want Maestro E2E flows for critical paths, so that releases are safe. | - Given a CI emulator, then flows for sign-in, quick-add, complete task and breakdown pass - Flows run on every PR to main in under 12 minutes - Flaky tests are quarantined and tracked, not ignored | P1 | 5 | Wave 4 | WS-E | 5 | Phase 2 | US-013, US-015, US-002 | Draft
US-039 | EP-13 | FT-37 | Data export and account deletion | As a user, I want to export my data and delete my account, so that I control my information. | - Given Settings > Account, when I request export, then a JSON file of my tasks is generated and shared via the OS share sheet - Given I confirm deletion, then my server data and AI usage rows are deleted within 24 hours and I am signed out - The flow is reachable in 3 taps and satisfies store account-deletion rules | P0 | 5 | Wave 4 | WS-B | 6 | Phase 2 | US-029, US-006 | Draft
US-040 | EP-13 | FT-37 | Privacy policy, terms and AI disclosure | As the product owner, I want privacy policy, terms and AI disclosure, so that the app is compliant for store review. | - Privacy policy and terms are published at stable URLs and linked in Settings and on sign-in - The policy states what text/audio/images are sent to an AI provider, retention, and deletion - App Store privacy labels and Play data-safety form drafts are prepared | P0 | 2 | Wave 4 | WS-D | 6 | Phase 2 | - | Draft
US-041 | EP-09 | FT-25 | Buddy chat with confirmed actions | As a user, I want to chat with my buddy about my tasks, so that I can ask what to do next and make changes by talking. | - Given 'What should I do now?', then a streamed answer references my real tasks within 2 seconds to first token - Given 'Move my report to Friday', then the buddy proposes the change and applies it only after I tap Confirm - Conversation context sends a digest of at most 50 tasks and never other users' data | P1 | 8 | Wave 5 | WS-C | 6 | Phase 2 | US-010, US-009, US-011, US-012 | Draft
US-042 | EP-09 | FT-26 | Buddy tone and language (English/Taglish) | As a user, I want to choose the buddy's tone and language, so that it feels like mine. | - Given tone options Friendly, Coach, Chill and language English or Taglish, then check-ins and chat follow the selection - The setting syncs across devices - Eval set verifies each tone stays inside the safety rules | P3 | 3 | Wave 5 | WS-C | 6 | Phase 2 | US-041, US-018 | Draft
US-043 | EP-10 | FT-27 | Voice capture via speech recognition | As a user, I want to speak my tasks, so that I can capture hands-free. | - Given microphone permission, when I hold the mic and speak a sentence, then the transcript fills quick-add and is parsed like typed text - On-device recognition is used when available; the app states when a network service is used - Given unsupported locale or permission denied, then the app shows a clear fallback to typing | P1 | 5 | Wave 5 | WS-A | 6 | Phase 2 | US-015, US-016 | Draft
US-044 | EP-10 | FT-28 | Photo-to-tasks (vision extraction) | As a user, I want to photograph a handwritten list or whiteboard and get tasks, so that I can digitize paper. | - Given a photo of a 10-line list, then at least 90% of lines become task candidates in the review screen within 10 seconds - Images are resized to at most 1600 px and compressed before upload - I can crop or discard before anything is sent | P2 | 5 | Wave 5 | WS-A | 6 | Phase 2 | US-008, US-010, US-015 | Draft
US-045 | EP-10 | FT-29 | Media upload limits, consent and auto-deletion | As a user, I want my photos and audio handled privately, so that sensitive notes are safe. | - Given an uploaded image or audio file, then the raw media is deleted from storage within 24 hours - A one-time consent explains that images are processed by an AI provider - Uploads over 5 MB or 60 seconds are rejected with a friendly error | P1 | 3 | Wave 5 | WS-C | 7 | Phase 2 | US-044, US-043 | Draft
US-046 | EP-11 | FT-30 | Weekly completion statistics | As a user, I want weekly stats of what I completed and slipped, so that I can see my progress. | - Given a week of activity, then the stats screen shows completed count, slipped count, on-time rate and best day - Numbers equal an independent SQL calculation in tests - Stats compute locally without an AI call | P2 | 3 | Wave 5 | WS-B | 7 | Phase 2 | US-013 | Draft
US-047 | EP-11 | FT-31 | AI weekly review and suggestion | As a user, I want an AI weekly review with wins and one suggestion, so that I improve each week. | - Given weekly stats, then a review with summary, up to 3 wins, up to 2 patterns and 1 suggestion generates in under 15 seconds - The review cites only numbers present in the stats payload (eval check) - A Sunday-evening notification offers the review when enabled | P2 | 5 | Wave 5 | WS-C | 7 | Phase 2 | US-046, US-010, US-009 | Draft
US-048 | EP-14 | FT-46 | Accessibility: labels, dynamic type, touch targets | As a user with accessibility needs, I want screen reader labels, dynamic type and sufficient targets, so that I can use the app. | - Given VoiceOver/TalkBack, then every interactive element has a label and a logical focus order on core screens - At 200% font scale, no text is clipped on Today, detail and quick-add - Touch targets are at least 44x44 pt | P1 | 3 | Wave 5 | WS-E | 7 | Phase 2 | US-013, US-014, US-015 | Draft
US-049 | EP-14 | FT-48 | Performance budgets for startup and lists | As a user, I want the app to open fast and scroll smoothly, so that it feels instant. | - Given a release build on a mid-range Android device, then cold start to interactive is under 2.5 seconds at p75 - A 1,000-task list scrolls with no dropped-frame spikes over 5% - Bundle size and startup time are tracked in CI with a regression budget | P2 | 3 | Wave 5 | WS-E | 7 | Phase 2 | US-013 | Draft
US-050 | EP-13 | FT-39 | v1.0 App Store and Google Play submission | As the product owner, I want v1.0 submitted to the App Store and Google Play, so that real users can install Task Buddy. | - Given store listings, screenshots and review notes with demo credentials, then both stores accept the submission - AI disclosure, privacy labels and account deletion are verified against the checklist - A rollback plan (OTA revert and previous build) is documented | P0 | 5 | Wave 5 | WS-D | 7 | Phase 2 | US-024, US-040, US-039, US-037, US-048, US-038 | Draft
US-051 | EP-14 | FT-47 | Consent-gated product analytics | As the product owner, I want privacy-respecting product analytics, so that I can see activation and retention. | - Given consent, then events (task_created, ai_used, plan_accepted) flow to PostHog with no task text - Without consent no events are sent - A funnel dashboard exists for signup to first AI use | P2 | 3 | Wave 5 | WS-D | 7 | Phase 2 | US-004, US-018 | Draft
US-052 | EP-14 | FT-46 | Filipino and English UI localization | As a Filipino user, I want the UI in Filipino or English, so that it feels natural. | - Given language set to Filipino, then all static strings display translated and layouts do not overflow - Strings live in resource files and a missing key fails CI - Dates and numbers follow the locale | P3 | 3 | Wave 5 | WS-A | 7 | Phase 2 | US-004, US-018 | Draft
US-053 | EP-03 | FT-09 | Full-text task search (FTS5) | As a user, I want fast full-text search, so that I can find any task. | - Given 5,000 tasks, then search results appear within 100 ms of typing using SQLite FTS5 - Search covers title, notes and subtasks - Results update after edits without a restart | P2 | 3 | Wave 6 | WS-B | 8 | Phase 3 | US-030 | Draft
US-054 | EP-12 | FT-32 | Shared spaces: membership, roles, RLS | As a user, I want to create a shared space with members and roles, so that a team or family can collaborate. | - Given a new space, then I am its owner and can see it in my spaces list - RLS tests prove a non-member can never read a space's tasks, members or comments - Roles owner, editor and viewer are enforced at the database level | P1 | 5 | Wave 6 | WS-B | 8 | Phase 3 | US-029, US-006 | Draft
US-055 | EP-12 | FT-35 | Agent scopes and confirmations (server-enforced) | As a space owner, I want to control what the AI agent may do, so that it cannot act beyond my intent. | - Given agent scopes (read tasks, propose changes, apply changes), then the agent cannot exceed the scope set by the owner - Every state-changing agent action requires a human confirmation unless the owner enables auto-apply per scope - Scopes are enforced server-side in the gateway, not only in the UI | P1 | 5 | Wave 6 | WS-C | 8 | Phase 3 | US-054, US-008 | Draft
US-056 | EP-12 | FT-32 | Space invites by link or code | As a space owner, I want to invite people by link or code, so that joining is easy and safe. | - Given an invite link, when an invitee opens it signed in, then they join with the role set by the owner - Invites expire after 7 days and can be revoked - Owners can remove members and removed members lose access immediately | P1 | 5 | Wave 6 | WS-B | 8 | Phase 3 | US-054 | Draft
US-057 | EP-12 | FT-33 | Realtime shared lists | As a member, I want shared task lists that update in real time, so that everyone sees the same truth. | - Given two members online, when one completes a task, then the other sees it within 2 seconds - Offline edits merge through sync with no lost updates (automated two-client test) - Realtime channels are scoped per space and unsubscribed on leave | P1 | 8 | Wave 6 | WS-B | 8 | Phase 3 | US-054, US-012, US-029 | Draft
US-058 | EP-12 | FT-33 | Task assignment and comments | As a member, I want to assign tasks and comment on them, so that work is coordinated. | - Given a shared task, when I assign it to a member, then they see it in My Tasks and are notified - Comments are ordered, editable by the author for 15 minutes, and visible to all members - Mentions notify the mentioned member only | P2 | 5 | Wave 6 | WS-A | 9 | Phase 3 | US-057 | Draft
US-059 | EP-12 | FT-33 | Space notifications and muting | As a member, I want notifications for assignments and mentions, so that I do not miss shared work. | - Given I am assigned or mentioned, then I receive a push within 30 seconds unless in quiet hours - Notifications are grouped per space and can be muted per space - Muted spaces send nothing | P2 | 3 | Wave 6 | WS-C | 9 | Phase 3 | US-057, US-032 | Draft
US-060 | EP-12 | FT-34 | Shared AI agent via @buddy in spaces | As a member, I want to @mention the buddy in a space, so that the AI can summarize, suggest and propose changes using shared context. | - Given '@buddy what is blocking us this week?', then the agent answers from the space's tasks and comments only - Given a proposed change, then it appears as a pending proposal that a member with permission can approve or reject - The agent never reads other spaces or private tasks (isolation test) | P1 | 8 | Wave 6 | WS-C | 9 | Phase 3 | US-057, US-055, US-010, US-009, US-041 | Draft
US-061 | EP-12 | FT-35 | Agent action audit log | As a space owner, I want an audit log of everything the agent did, so that I can trust and review it. | - Given any agent proposal or action, then a log row records who requested it, scope, input digest, result and approver - Owners can view and filter the log in the app - Logs are immutable to members and retained 90 days | P1 | 3 | Wave 6 | WS-B | 9 | Phase 3 | US-055, US-060 | Draft
US-062 | EP-12 | FT-34 | AI workload-balancing proposals | As a space owner, I want the AI to suggest how to balance workload across members, so that no one is overloaded. | - Given open tasks and member capacity, then the agent proposes assignments with a one-line reason each - Nothing is assigned until a human approves each proposal - Proposals respect member work hours and existing assignments | P2 | 5 | Wave 6 | WS-C | 9 | Phase 3 | US-060, US-058 | Draft
US-063 | EP-13 | FT-36 | Pro subscription via RevenueCat | As a user, I want to upgrade to Pro, so that I get higher AI limits and Spaces. | - Given a purchase in the sandbox, then the Pro entitlement activates within 10 seconds and survives reinstall (restore purchases) - A server webhook updates the subscription table and the entitlement is checked server-side - Cancelling returns the account to Free at period end | P2 | 8 | Wave 6 | WS-B | 10 | Phase 3 | US-006, US-009 | Draft
US-064 | EP-13 | FT-36 | Tier-based AI quotas | As the product owner, I want quotas that depend on tier, so that cost scales with revenue. | - Given Free and Pro tiers, then the gateway applies each tier's hourly and daily limits from config - A Pro user is not blocked at the free limit - Tier changes apply on the next request | P2 | 3 | Wave 6 | WS-C | 10 | Phase 3 | US-063, US-009 | Draft
US-065 | EP-13 | FT-40 | Calendar-aware planning (busy times only) | As a user, I want the planner to see my calendar events, so that plans avoid meetings. | - Given calendar permission, then busy blocks for today are excluded from planning windows - Only busy/free times are sent to the AI, never event titles or attendees - Denying permission leaves planning unchanged | P3 | 5 | Wave 6 | WS-A | 10 | Phase 3 | US-020, US-018 | Draft
US-066 | EP-13 | FT-41 | Home-screen Today widget | As a user, I want a home-screen widget showing today's top tasks, so that I see them without opening the app. | - Given the widget, then it shows up to 3 top tasks and refreshes after changes within 15 minutes - Tapping a task deep-links to its detail - iOS and Android availability is documented per platform | P3 | 5 | Wave 6 | WS-A | 10 | Phase 3 | US-013, US-021 | Draft
US-067 | EP-04 | FT-42 | Experimental on-device parsing | As a privacy-minded user, I want offline task parsing on my device, so that capture works without internet and without sending text. | - Given airplane mode, then quick-add parses simple sentences locally and falls back to plain add when confidence is low - The local model download is optional, shows its size, and can be removed - On the golden set the local parser reaches at least 75% accuracy and the gap vs cloud is reported | P3 | 8 | Wave 6 | WS-C | 10 | Phase 3 | US-016, US-010, US-025 | Draft
[6 empty] | Total | 279

## Sprint Backlog
Sprint # | Start | End | Goal | Stories | Est. Points | Capacity | Utilization | Depends on (earlier sprints) | Deliverables
1 | 2026-11-02 | 2026-11-06 | Foundations: scaffold, CI, design system, shell, Supabase, email sign-in, local DB, and the AI gateway with rate limits and output contracts. | US-001, US-002, US-003, US-004, US-005, US-006, US-007, US-008, US-009, US-010 | 30 | 30 | 100% | - | Bootable app, CI, design system, Supabase, email sign-in, local DB, AI gateway with limits and schemas
2 | 2026-11-09 | 2026-11-13 | MVP complete: injection hardening, task CRUD and Today/Inbox/detail screens, natural-language quick-add, AI task breakdown, settings shell. | US-011, US-012, US-013, US-014, US-015, US-016, US-017, US-018 | 30 | 30 | 100% | US-004, US-007, US-008, US-009, US-010 | Working MVP: tasks, Today/Inbox, quick-add parse, AI breakdown, settings shell
3 | 2026-11-16 | 2026-11-20 | Daily plan (work hours, generation, plan UI), undo for AI tasks, crash reporting, first TestFlight/Play beta and AI evals. | US-019, US-020, US-021, US-022, US-023, US-024, US-025 | 28 | 30 | 93.33% | US-001, US-002, US-009, US-010, US-012, US-013, US-015, US-016, US-017, US-018 | Daily plan, undo, Sentry, first beta build, eval harness
4 | 2026-11-23 | 2026-11-27 | Retention: reminders, permission flow, re-plan, offline sync, lists/tags, recurring tasks. | US-026, US-027, US-028, US-029, US-030, US-031 | 27 | 30 | 90% | US-006, US-007, US-012, US-018, US-021 | Reminders, offline sync, lists/tags, recurring, re-plan
5 | 2026-11-30 | 2026-12-04 | Push infrastructure, buddy check-ins, procrastination helper, social sign-in, onboarding, E2E tests. | US-032, US-033, US-034, US-035, US-036, US-037, US-038 | 29 | 30 | 96.67% | US-002, US-006, US-008, US-009, US-010, US-013, US-014, US-015, US-018, US-019, US-020, US-026, US-027 | Push + check-ins, procrastination helper, onboarding, E2E suite
6 | 2026-12-07 | 2026-12-11 | Compliance and buddy chat: data export/deletion, privacy docs, chat, personality, voice, photo. | US-039, US-040, US-041, US-042, US-043, US-044 | 28 | 30 | 93.33% | US-006, US-008, US-009, US-010, US-011, US-012, US-015, US-016, US-018, US-029 | Account deletion/export, privacy docs, buddy chat, voice, photo
7 | 2026-12-14 | 2026-12-18 | Media privacy, weekly review, accessibility, performance, analytics, i18n and the v1.0 store release. | US-045, US-046, US-047, US-048, US-049, US-050, US-051, US-052 | 28 | 30 | 93.33% | US-004, US-009, US-010, US-013, US-014, US-015, US-018, US-024, US-037, US-038, US-039, US-040, US-043, US-044 | Weekly review, accessibility, performance, v1.0 store submission
8 | 2026-12-21 | 2026-12-25 | Search and the Shared Spaces foundation: membership, agent permissions, invites, realtime shared lists. | US-053, US-054, US-055, US-056, US-057 | 26 | 30 | 86.67% | US-006, US-008, US-012, US-029, US-030 | Spaces foundation, agent permissions, realtime shared lists, search
9 | 2026-12-28 | 2027-01-01 | Shared Spaces collaboration and the shared AI agent: assignment, notifications, agent, audit, balancing. | US-058, US-059, US-060, US-061, US-062 | 24 | 30 | 80% | US-009, US-010, US-032, US-041, US-055, US-057 | Assignment/comments, space agent, audit log, workload balancing
10 | 2027-01-04 | 2027-01-08 | Monetization and extras: billing, tier quotas, calendar, widgets, experimental on-device AI. | US-063, US-064, US-065, US-066, US-067 | 29 | 30 | 96.67% | US-006, US-009, US-010, US-013, US-016, US-018, US-020, US-021, US-025 | Billing and tier quotas, calendar, widgets, experimental on-device AI
|  |  |  | Sum of sprint points | 279
|  |  |  | Sum of backlog points | 279
|  |  |  | Difference (must be 0) | 0
Capacity is an assumption: solo developer with AI coding agents, 1-week sprints. Edit the blue capacity cells to re-check utilization.

## Technical Backlog
Task ID | Category | Task | Epic | Linked Story | Wave | Sprint | Status
TT-01 | Infra | Create GitHub repo, protect main, require CI + 1 review | EP-01 | US-001 | Wave 1 | 1 | Draft
TT-02 | Infra | Provision Supabase dev/staging/prod projects and EAS env | EP-02 | US-005 | Wave 1 | 1 | Draft
TT-03 | Infra | Create EAS project, credentials and build profiles (development/preview/production) | EP-01 | US-002 | Wave 1 | 1 | Draft
TT-04 | DB | Drizzle SQLite schema v1 and migration runner | EP-03 | US-007 | Wave 1 | 1 | Draft
TT-05 | DB | Postgres schema v1 migrations plus RLS policies for profiles | EP-02 | US-005 | Wave 1 | 1 | Draft
TT-06 | DB | Add sync columns and triggers (updated_at, deleted_at, server_seq) | EP-03 | US-029 | Wave 4 | 4 | Draft
TT-07 | DB | pg_cron + pg_net schedule for check-ins and token cleanup | EP-08 | US-033 | Wave 4 | 5 | Draft
TT-08 | DB | Spaces, members, comments, agent_actions tables with RLS | EP-12 | US-054 | Wave 6 | 8 | Draft
TT-09 | API | Edge Function ai-gateway router and provider interface | EP-04 | US-008 | Wave 2 | 1 | Draft
TT-10 | API | Shared Zod schema package used by app and functions | EP-04 | US-010 | Wave 2 | 1 | Draft
TT-11 | API | sync_pull and sync_push RPCs with conflict rules | EP-03 | US-029 | Wave 4 | 4 | Draft
TT-12 | API | revenuecat-webhook function and subscription table | EP-13 | US-063 | Wave 6 | 10 | Draft
TT-13 | FE | NativeWind theme and tokens, dark mode | EP-01 | US-003 | Wave 1 | 1 | Draft
TT-14 | FE | Task repository hooks with TanStack Query and optimistic updates | EP-03 | US-012 | Wave 2 | 2 | Draft
TT-15 | FE | Undo store and toast component | EP-05 | US-022 | Wave 3 | 3 | Draft
TT-16 | FE | Notification categories with quick-reply actions | EP-08 | US-033 | Wave 4 | 5 | Draft
TT-17 | BE | Versioned prompt templates in repo with eval hooks | EP-04 | US-010 | Wave 2 | 1 | Draft
TT-18 | BE | Usage ledger table and quota check function | EP-04 | US-009 | Wave 2 | 1 | Draft
TT-19 | BE | Per-route model routing config (cheap model for parse, stronger for plan/review) | EP-04 | US-008 | Wave 2 | 1 | Draft
TT-20 | Security | RLS automated test suite (pgTAP or SQL tests) | EP-02 | US-005 | Wave 1 | 1 | Draft
TT-21 | Security | Secrets management and key rotation runbook | EP-04 | US-008 | Wave 2 | 1 | Draft
TT-22 | Security | Prompt-injection test corpus (20+ cases) in CI | EP-04 | US-011 | Wave 2 | 2 | Draft
TT-23 | Security | Agent scope enforcement middleware in gateway | EP-12 | US-055 | Wave 6 | 8 | Draft
TT-24 | DevOps | GitHub Actions: lint, typecheck, unit, eval, E2E workflows | EP-01 | US-002 | Wave 1 | 1 | Draft
TT-25 | DevOps | EAS Update channels per environment and rollback procedure | EP-13 | US-024 | Wave 3 | 3 | Draft
TT-26 | DevOps | Supabase CLI migration pipeline from PR to staging to prod | EP-02 | US-005 | Wave 1 | 1 | Draft
TT-27 | Monitoring | Sentry init, source map upload, PII scrubbing | EP-14 | US-023 | Wave 3 | 3 | Draft
TT-28 | Monitoring | PostHog event taxonomy and consent gate | EP-14 | US-051 | Wave 5 | 7 | Draft
TT-29 | Monitoring | AI cost dashboard (SQL view) with daily spend alert | EP-04 | US-009 | Wave 2 | 1 | Draft

## Architecture & Decisions
Area | Decision | Rationale | Alternatives considered
Client framework | Expo (latest stable SDK) + React Native, TypeScript strict, Expo Router | Fast iteration, OTA updates, one codebase; Expo SDK 56 (May 2026) confirmed stable, SDK 57 is listed on expo.dev/sdk - use latest stable at scaffold | Bare React Native, Flutter
Styling | NativeWind (Tailwind for RN) with token theme | Utility styling, dark mode, fast UI work | StyleSheet only, Tamagui, Unistyles
Client state | Zustand for UI state, TanStack Query for async/server state | Small, predictable, well supported | Redux Toolkit, Jotai
Forms/validation | React Hook Form + Zod (shared schemas) | One schema validates app input and AI output | Formik, Yup
Local database | expo-sqlite + Drizzle ORM | Offline-first, typed queries, FTS5 for search | WatermelonDB, MMKV-only, Realm
Backend platform | Supabase (Postgres, Auth, Realtime, Storage, Edge Functions) | One platform for auth, data, realtime and server code; RLS for isolation | Firebase, custom Node API
Sync | Custom last-write-wins sync over RPC with tombstones (v1); revisit CRDT for Spaces | Simple and testable for single-user data; Spaces need stronger guarantees | PowerSync, ElectricSQL, Replicache
AI provider | Claude via Edge Function gateway; cheaper model for parse/check-ins, stronger model for plan/review/chat | Keys server-side, cost control per route, structured outputs | Direct from client (rejected: key exposure)
AI output safety | JSON-schema validation + one repair retry + typed errors; actions always user-confirmed | Prevents bad data and unsafe actions | Free-text parsing
Voice input | expo-speech-recognition (on-device where available) feeding the same parser; cloud STT only as a later fallback | Free, private, no extra vendor; requires a development build and per-OS locale checks | Cloud STT from day one (cost, privacy)
Photo input | expo-image-picker/camera, resize on device, vision model through the gateway | Reuses the gateway and guardrails | Separate OCR vendor
Notifications | expo-notifications: local for reminders, Expo Push for server check-ins | Offline reliability for reminders, remote reach for nudges | OneSignal, FCM direct
Realtime (Spaces) | Supabase Realtime channels scoped per space | Native to the stack, RLS-aware | Custom WebSocket server
Billing | RevenueCat with webhook to Supabase | Handles store receipts and entitlements | Direct StoreKit/Play Billing
Observability | Sentry (crashes) + PostHog (product analytics, consent-gated) | Standard, cheap at small scale | Firebase Crashlytics
Testing | Jest + RNTL (unit), Maestro (E2E), custom eval runner (AI) | Covers logic, flows and AI regressions | Detox
CI/CD | GitHub Actions + EAS Build/Submit/Update | Matches Expo workflow | Bitrise, Codemagic
Widgets | Expo Widgets (iOS stable in SDK 56); Android widget approach decided in Phase 3 | Per Expo SDK 56 release notes | Native modules
On-device AI (experimental) | Evaluate ExecuTorch or llama.rn for offline parse in Phase 3 | Privacy/offline differentiator; needs eval gate | Skip

## Data Model
Entity / Table | Store | Key fields | Relationships | Access (RLS)
profiles | Postgres | id (uuid, = auth.users.id), display_name, timezone, locale, work_start, work_end, daily_capacity_min, buddy_tone, buddy_lang, onboarded_at | 1:1 auth.users | RLS: owner only
tasks | SQLite + Postgres | id (uuidv7), user_id, space_id (nullable), list_id, title, notes, due_at, priority, status, estimate_min, completed_at, postpone_count, source (manual/ai/voice/photo), rrule, parent_task_id, updated_at, deleted_at, server_seq | N:1 lists, N:1 spaces, self-ref parent | RLS: owner or space member by role
subtasks | SQLite + Postgres | id, task_id, title, done, estimate_min, position, updated_at, deleted_at | N:1 tasks | Inherits task access
lists | SQLite + Postgres | id, user_id, space_id, name, color, position, updated_at, deleted_at | 1:N tasks | RLS as tasks
tags / task_tags | SQLite + Postgres | tags(id, user_id, name); task_tags(task_id, tag_id) | M:N tasks-tags | Owner only
plans / plan_blocks | SQLite + Postgres | plans(id, user_id, date, accepted_at, model, prompt_version); plan_blocks(id, plan_id, task_id, start_at, end_at, pinned, reason) | 1:N | Owner only
device_tokens | Postgres | id, user_id, expo_push_token, platform, last_seen_at | N:1 users | Owner only; pruned on invalid receipt
notification_prefs | Postgres | user_id, quiet_start, quiet_end, checkins_enabled, daily_cap | 1:1 users | Owner only
ai_usage_ledger | Postgres | id, user_id, route, model, input_tokens, output_tokens, cost_usd_est, prompt_version, status, created_at | N:1 users | Insert by service role; owner can read own aggregate
weekly_reviews | Postgres | id, user_id, week_start, stats_json, review_json, created_at | N:1 users | Owner only
spaces / space_members | Postgres | spaces(id, name, owner_id, agent_scopes jsonb); space_members(space_id, user_id, role) | M:N users-spaces | RLS: members only
space_invites | Postgres | id, space_id, code_hash, role, expires_at, revoked_at | N:1 spaces | Owner/editor create; hashed codes
task_comments | Postgres | id, task_id, author_id, body, mentions[], created_at, edited_at | N:1 tasks | Space members
agent_actions | Postgres | id, space_id, requested_by, scope, input_digest, proposal_json, status (pending/approved/rejected/applied), approver_id, created_at | N:1 spaces | Members read; no member writes (service role)
subscriptions | Postgres | user_id, entitlement, product_id, period_end, store, updated_at | 1:1 users | Webhook writes; owner read

## API Contracts
Endpoint | Method | Description | Request | Response | Auth | Status codes | Story
/functions/v1/ai-gateway/parse | POST | Parse free text into tasks | { text, timezone, now, locale, lists[] } | { tasks: [{ title, dueAt, priority, list, notes, confidence }], promptVersion } | Supabase JWT | 200, 400, 401, 413, 429, 502 | US-016
/functions/v1/ai-gateway/breakdown | POST | Break a task into subtasks | { task: { id, title, notes, dueAt }, maxSubtasks } | { subtasks: [{ title, estimateMin }], totalMin } | Supabase JWT | 200, 400, 401, 429, 502 | US-017
/functions/v1/ai-gateway/plan | POST | Generate a daily plan | { date, timezone, workHours, capacityMin, tasks[], fixedBlocks[] } | { blocks: [{ taskId, startAt, endAt, reason }], unscheduled: [{ taskId, reason }] } | Supabase JWT | 200, 400, 401, 429, 502 | US-020
/functions/v1/ai-gateway/starter-step | POST | Suggest a tiny first step | { task, postponeCount, blockerNote? } | { step, estimateMin, encouragement } | Supabase JWT | 200, 400, 401, 429, 502 | US-035
/functions/v1/ai-gateway/chat | POST (SSE) | Streaming buddy chat with action proposals | { messages[], context: { tasksDigest[] } } | SSE events: text, proposal{ action, args } (never auto-applied) | Supabase JWT | 200, 401, 429, 502 | US-041
/functions/v1/ai-gateway/review | POST | Weekly review narrative | { weekStats, completed[], slipped[] } | { summary, wins[], patterns[], suggestion } | Supabase JWT | 200, 400, 401, 429, 502 | US-047
/functions/v1/ai-gateway/vision-extract | POST | Extract tasks from a photo | { storagePath, timezone } | { tasks[], rawText } | Supabase JWT | 200, 400, 401, 413, 429, 502 | US-044
/functions/v1/ai-gateway/space-agent | POST (SSE) | Shared agent in a space | { spaceId, message } | SSE: text, proposal rows written to agent_actions (pending) | Supabase JWT + space role + agent scope | 200, 401, 403, 429, 502 | US-060
rpc/sync_pull | POST | Fetch changes since a server sequence | { since_seq } | { rows[], next_seq } | Supabase JWT | 200, 401 | US-029
rpc/sync_push | POST | Push local changes | { ops[] } | { accepted[], conflicts[] } | Supabase JWT | 200, 401, 409 | US-029
/functions/v1/send-checkins | POST (cron) | Generate and send check-ins | service-role internal | { sent, skipped } | Service role only | 200 | US-033
/functions/v1/revenuecat-webhook | POST | Update subscription state | RevenueCat event | { ok } | Shared secret header | 200, 401 | US-063
rpc/create_invite, rpc/accept_invite | POST | Create and redeem space invites | { spaceId, role } / { code } | { code } / { spaceId, role } | Supabase JWT | 200, 403, 404, 410 | US-056
rpc/export_my_data, rpc/delete_my_account | POST | Data export and account deletion | {} | { file } / { ok } | Supabase JWT | 200, 401 | US-039

## QA & Testing
Epic / Feature | Unit | Integration | E2E | Regression | UAT | Edge & error cases | Security cases
EP-01 Foundations | Lint/typecheck rules; helper tests | CI pipeline dry run | Smoke boot on iOS+Android | Run full CI on main nightly | Fresh-clone install on a clean machine | Missing env var fails loudly | No secrets committed (secret scan)
EP-02 Auth | Session store; OTP form validation | Sign in against staging Supabase | Sign in, restart, still signed in | Auth after app update | Sign in with 3 testers | Expired/wrong OTP, no network | RLS cross-user tests; token storage in secure store
EP-03 Task core & sync | Repositories; RRULE edge cases; conflict resolver | SQLite migrations; sync pull/push against staging | Create/complete/delete; two-device sync | Task counts before/after upgrade | Daily use for 1 week | Airplane mode, clock skew, DST, 10k tasks | RLS on tasks; tombstone handling
EP-04 AI gateway | Schema validators; quota math | Gateway with mocked provider | Quick-add happy path | Rate limit and quota behavior | Beta user cost review | Provider timeout, 429, malformed JSON | Injection corpus; key not in bundle; JWT required
EP-05 Capture | Parse result mapping | Parse with golden set | Type sentence, review, save | Eval pass rate vs baseline | 5 testers type real tasks | Ambiguous dates, emoji, 2,000-char input | Prompt isolation
EP-06 Breakdown | Subtask merge logic | Breakdown golden set | Break down, accept some, regenerate | Eval baseline | Testers rate usefulness 1-5 | One-word task, very long task | Output sanitized before render
EP-07 Daily plan | Capacity math, overlap checks | Plan golden set; re-plan | Generate, reorder, accept | Plan constraints never violated | Testers follow a plan for 3 days | No tasks, all tasks overdue, DST day | No other user data in prompt
EP-08 Notifications | Quiet-hours logic | Local schedule; push send to sandbox | Reminder fires; quick action works | Cancel on complete/delete | Real devices over 3 days | Permission denied, token invalid, timezone change | Daily push cap server-side
EP-09 Buddy chat & helper | Proposal parser | Chat with mocked provider | Chat proposes then confirms change | Eval tone/safety set | Testers try 10 prompts | Long history, offline mid-stream | Actions require confirm; injection via task titles
EP-10 Voice & photo | Image resize; locale mapping | Upload and delete job | Speak a task; photo a list | Deletion within 24h | Taglish speakers test | Noisy audio, blurry photo, unsupported locale | Media deletion; consent captured
EP-11 Weekly review | Stats SQL equals JS | Review generation | Open review on Sunday | Numbers match stats | Testers read two reviews | Empty week | No hallucinated numbers
EP-12 Shared Spaces | Role checks; merge rules | RLS suite; realtime two-client test | Invite, join, assign, comment | Isolation between spaces | Pilot with 2 small teams | Offline edits, removed member, expired invite | Cross-space isolation; agent scope enforcement; audit immutability
EP-13 Compliance & billing | Entitlement mapping | Webhook to subscriptions | Purchase, restore, cancel (sandbox) | Quota tier switching | Store review dry run | Refund, restore on new device | Account deletion completeness
EP-14 Quality | Eval runner | CI gating | Maestro critical flows | Perf budget checks | Accessibility audit with screen reader | 200% font, low-end Android | PII scrubbing in Sentry

## DevOps & Deploy
Area | Approach
Repository | Single GitHub repo (app + supabase/ functions + migrations + docs); pnpm workspaces for shared packages
Branching | Trunk-based; branches `<type>/tb-<ticket>/<short-kebab-title>`; squash-merge; Conventional Commits `feat(scope): summary (TB-###)`
CI | GitHub Actions: lint, typecheck, unit tests, secret scan, AI evals on prompt/model changes, Maestro on main
CD (app) | EAS Build for native changes; EAS Update (OTA) for JS-only changes via development/preview/production channels; EAS Submit to TestFlight/Play
CD (backend) | Supabase CLI migrations PR -> staging -> prod; Edge Functions deployed from CI
Environments | dev (local + Supabase dev), staging (internal testers), prod; separate Supabase projects and EAS env
Secrets | LLM key and service-role key only in Supabase secrets/CI secrets; never in app bundle
Monitoring | Sentry crashes and release health; Supabase logs; AI cost dashboard with daily spend alert
Logging | Structured logs with request id; no task text in logs; AI requests log metadata only
Backup | Supabase point-in-time recovery enabled on prod; weekly export of ledger tables
Disaster recovery | Restore PITR to new project; OTA rollback to last good update; previous store build kept available; RTO 4h, RPO 15 min (targets)
Release process | Beta weekly; production release after checklist: E2E green, eval baseline met, privacy labels verified

## Risk Register
Risk | Impact | Probability | Mitigation | Owner
AI cost grows faster than revenue | High | Medium | Per-user rate limits and quotas (US-009), cheap model for parse, usage ledger and spend alert, tiered quotas | Owner
Prompt injection or unsafe AI actions | High | Medium | Input caps, schema validation, no server-side action execution, user confirmation, injection corpus in CI | Owner
AI output quality regresses silently | Medium | Medium | Golden sets and CI regression gate (US-025) | Owner
Data loss or duplicates during sync | High | Medium | Tombstones, two-client tests, soft deletes, backups | Owner
App Store rejection (AI disclosure, account deletion, sign-in rules) | Medium | Medium | Compliance stories before release; Sign in with Apple when social sign-in exists | Owner
Solo-capacity slip (velocity below 30) | Medium | High | MVP scope cut order: breakdown, then edit/undo; weekly re-plan of sprints | Owner
Speech recognition quality for Taglish | Medium | Medium | Test locales early; allow typing fallback; evaluate cloud STT fallback | Owner
Cross-space data leak in Shared Spaces | High | Low | RLS tests, agent scope enforcement server-side, isolation tests | Owner
Notification fatigue causes uninstalls | Medium | Medium | Daily cap, quiet hours, user-controlled frequency | Owner
Expo SDK / library breaking changes (e.g. Router migration) | Medium | Medium | Pin versions, upgrade per SDK with a dedicated ticket, use Expo skills for upgrades | Owner
Privacy concerns about sending tasks to an AI provider | Medium | Medium | Clear disclosure, consent, deletion controls, on-device option (US-067) | Owner
Widget/native feature availability differs by platform | Low | Medium | Document per-platform support; ship iOS first | Owner

## Future Improvements
Category | Idea
Nice-to-have | Natural-language search ('what did I plan for the dentist?')
Nice-to-have | Habit streaks and gentle gamification
Scalability | CRDT-based sync for Spaces; move heavy jobs to queues
Performance | Local embeddings for semantic search
Security | E2E encryption option for private lists
AI | Proactive agent that drafts next-day plan overnight
AI | Per-user learned estimation (actual vs estimated time)
Mobile | Apple Watch / Wear OS quick capture
Mobile | Share-sheet extension to create tasks from any app
Mobile | Lock-screen and Live Activity for current task
Integrations | Email-to-task, Google/Outlook calendar sync, Slack
Platform | Public API and automations for Spaces

## PM Import
Level | ID | Parent ID | Issue Type | Summary | Priority | Points | Wave | Workstream | Sprint | Labels
Initiative | TB-INIT | - | Initiative | Task Buddy v1.0 and Shared Spaces | P0 |  |  |  |  | task-buddy
Epic | EP-01 | TB-INIT | Epic | Foundations & DevOps | P0 |  | Wave 1 |  |  | epic-ep-01
Epic | EP-02 | TB-INIT | Epic | Auth & Accounts | P0 |  | Wave 1 |  |  | epic-ep-02
Epic | EP-03 | TB-INIT | Epic | Task Core & Sync | P0 |  | Wave 1-4 |  |  | epic-ep-03
Epic | EP-04 | TB-INIT | Epic | AI Gateway & Guardrails | P0 |  | Wave 2 |  |  | epic-ep-04
Epic | EP-05 | TB-INIT | Epic | Natural-Language Capture | P0 |  | Wave 3 |  |  | epic-ep-05
Epic | EP-06 | TB-INIT | Epic | AI Task Breakdown | P1 |  | Wave 3 |  |  | epic-ep-06
Epic | EP-07 | TB-INIT | Epic | Smart Daily Plan | P1 |  | Wave 3-4 |  |  | epic-ep-07
Epic | EP-08 | TB-INIT | Epic | Notifications & Buddy Check-ins | P1 |  | Wave 4 |  |  | epic-ep-08
Epic | EP-09 | TB-INIT | Epic | Procrastination Helper & Buddy Chat | P1 |  | Wave 4-5 |  |  | epic-ep-09
Epic | EP-10 | TB-INIT | Epic | Voice & Photo Capture | P1 |  | Wave 5 |  |  | epic-ep-10
Epic | EP-11 | TB-INIT | Epic | Weekly Review & Insights | P2 |  | Wave 5 |  |  | epic-ep-11
Epic | EP-12 | TB-INIT | Epic | Shared Spaces (Multiplayer AI) | P2 |  | Wave 6 |  |  | epic-ep-12
Epic | EP-13 | TB-INIT | Epic | Monetization, Compliance & Release | P0 |  | Wave 3-6 |  |  | epic-ep-13
Epic | EP-14 | TB-INIT | Epic | Quality, Observability & Accessibility | P1 |  | Wave 3-5 |  |  | epic-ep-14
Feature | FT-01 | EP-01 | Feature (label) | Project scaffold & tooling | P0 |  |  |  |  | feature-ft-01
Feature | FT-02 | EP-01 | Feature (label) | CI/CD & build profiles | P0 |  |  |  |  | feature-ft-02
Feature | FT-03 | EP-01 | Feature (label) | Design system & navigation shell | P0 |  |  |  |  | feature-ft-03
Feature | FT-06 | EP-02 | Feature (label) | Supabase backend baseline | P0 |  |  |  |  | feature-ft-06
Feature | FT-04 | EP-02 | Feature (label) | Email OTP sign-in | P0 |  |  |  |  | feature-ft-04
Feature | FT-05 | EP-02 | Feature (label) | Social sign-in | P2 |  |  |  |  | feature-ft-05
Feature | FT-49 | EP-02 | Feature (label) | Settings & preferences | P1 |  |  |  |  | feature-ft-49
Feature | FT-07 | EP-03 | Feature (label) | Local data layer | P0 |  |  |  |  | feature-ft-07
Feature | FT-08 | EP-03 | Feature (label) | Task management UI | P0 |  |  |  |  | feature-ft-08
Feature | FT-09 | EP-03 | Feature (label) | Organization | P2 |  |  |  |  | feature-ft-09
Feature | FT-10 | EP-03 | Feature (label) | Recurring tasks | P2 |  |  |  |  | feature-ft-10
Feature | FT-11 | EP-03 | Feature (label) | Offline-first sync | P1 |  |  |  |  | feature-ft-11
Feature | FT-12 | EP-04 | Feature (label) | AI gateway | P0 |  |  |  |  | feature-ft-12
Feature | FT-13 | EP-04 | Feature (label) | Usage guardrails | P0 |  |  |  |  | feature-ft-13
Feature | FT-14 | EP-04 | Feature (label) | Output contracts & safety | P0 |  |  |  |  | feature-ft-14
Feature | FT-42 | EP-04 | Feature (label) | On-device inference (experimental) | P3 |  |  |  |  | feature-ft-42
Feature | FT-15 | EP-05 | Feature (label) | Quick-add parse | P0 |  |  |  |  | feature-ft-15
Feature | FT-16 | EP-05 | Feature (label) | Review & undo | P1 |  |  |  |  | feature-ft-16
Feature | FT-17 | EP-06 | Feature (label) | Breakdown | P1 |  |  |  |  | feature-ft-17
Feature | FT-18 | EP-07 | Feature (label) | Work hours | P1 |  |  |  |  | feature-ft-18
Feature | FT-19 | EP-07 | Feature (label) | Plan generation | P1 |  |  |  |  | feature-ft-19
Feature | FT-20 | EP-07 | Feature (label) | Plan UI & re-plan | P1 |  |  |  |  | feature-ft-20
Feature | FT-21 | EP-08 | Feature (label) | Reminders | P1 |  |  |  |  | feature-ft-21
Feature | FT-22 | EP-08 | Feature (label) | Push infrastructure | P1 |  |  |  |  | feature-ft-22
Feature | FT-23 | EP-08 | Feature (label) | Buddy check-ins | P1 |  |  |  |  | feature-ft-23
Feature | FT-24 | EP-09 | Feature (label) | Procrastination helper | P2 |  |  |  |  | feature-ft-24
Feature | FT-25 | EP-09 | Feature (label) | Buddy chat | P1 |  |  |  |  | feature-ft-25
Feature | FT-26 | EP-09 | Feature (label) | Personality | P3 |  |  |  |  | feature-ft-26
Feature | FT-27 | EP-10 | Feature (label) | Voice capture | P1 |  |  |  |  | feature-ft-27
Feature | FT-28 | EP-10 | Feature (label) | Photo capture | P2 |  |  |  |  | feature-ft-28
Feature | FT-29 | EP-10 | Feature (label) | Media privacy | P1 |  |  |  |  | feature-ft-29
Feature | FT-30 | EP-11 | Feature (label) | Weekly stats | P2 |  |  |  |  | feature-ft-30
Feature | FT-31 | EP-11 | Feature (label) | AI weekly review | P2 |  |  |  |  | feature-ft-31
Feature | FT-32 | EP-12 | Feature (label) | Spaces & membership | P2 |  |  |  |  | feature-ft-32
Feature | FT-33 | EP-12 | Feature (label) | Shared lists realtime | P2 |  |  |  |  | feature-ft-33
Feature | FT-34 | EP-12 | Feature (label) | Shared AI agent | P2 |  |  |  |  | feature-ft-34
Feature | FT-35 | EP-12 | Feature (label) | Agent permissions & audit | P1 |  |  |  |  | feature-ft-35
Feature | FT-36 | EP-13 | Feature (label) | Subscription | P2 |  |  |  |  | feature-ft-36
Feature | FT-37 | EP-13 | Feature (label) | Compliance | P0 |  |  |  |  | feature-ft-37
Feature | FT-38 | EP-13 | Feature (label) | Onboarding | P1 |  |  |  |  | feature-ft-38
Feature | FT-39 | EP-13 | Feature (label) | Beta & store release | P0 |  |  |  |  | feature-ft-39
Feature | FT-40 | EP-13 | Feature (label) | Calendar integration | P3 |  |  |  |  | feature-ft-40
Feature | FT-41 | EP-13 | Feature (label) | Widgets | P3 |  |  |  |  | feature-ft-41
Feature | FT-43 | EP-14 | Feature (label) | Observability | P1 |  |  |  |  | feature-ft-43
Feature | FT-44 | EP-14 | Feature (label) | E2E testing | P1 |  |  |  |  | feature-ft-44
Feature | FT-45 | EP-14 | Feature (label) | AI evals | P1 |  |  |  |  | feature-ft-45
Feature | FT-46 | EP-14 | Feature (label) | Accessibility & i18n | P1 |  |  |  |  | feature-ft-46
Feature | FT-47 | EP-14 | Feature (label) | Analytics | P2 |  |  |  |  | feature-ft-47
Feature | FT-48 | EP-14 | Feature (label) | Performance | P2 |  |  |  |  | feature-ft-48
Story | US-001 | EP-01 | Story | Scaffold Expo app (TypeScript, Router, lint, aliases) | P0 | 3 | Wave 1 | WS-D | 1 | ft-01 mvp
Story | US-002 | EP-01 | Story | CI pipeline and EAS build profiles | P0 | 3 | Wave 1 | WS-D | 1 | ft-02 mvp
Story | US-003 | EP-01 | Story | Design system: theme tokens and UI primitives | P0 | 3 | Wave 1 | WS-A | 1 | ft-03 mvp
Story | US-004 | EP-01 | Story | App shell: tab navigation and task modal | P0 | 2 | Wave 1 | WS-A | 1 | ft-03 mvp
Story | US-005 | EP-02 | Story | Supabase projects, env config and RLS baseline | P0 | 2 | Wave 1 | WS-B | 1 | ft-06 mvp
Story | US-006 | EP-02 | Story | Email OTP sign-in with secure session | P0 | 3 | Wave 1 | WS-B | 1 | ft-04 mvp
Story | US-007 | EP-03 | Story | Local SQLite schema, migrations and repositories | P0 | 3 | Wave 1 | WS-B | 1 | ft-07 mvp
Story | US-008 | EP-04 | Story | AI gateway Edge Function with JWT auth | P0 | 5 | Wave 2 | WS-C | 1 | ft-12 mvp
Story | US-009 | EP-04 | Story | Per-user AI rate limits and token quotas | P0 | 3 | Wave 2 | WS-C | 1 | ft-13 mvp
Story | US-010 | EP-04 | Story | AI output schemas, validation and repair retry | P0 | 3 | Wave 2 | WS-C | 1 | ft-14 mvp
Story | US-011 | EP-04 | Story | Prompt-injection and input hardening | P0 | 2 | Wave 2 | WS-C | 2 | ft-14 mvp
Story | US-012 | EP-03 | Story | Task CRUD with due date and priority | P0 | 5 | Wave 2 | WS-A | 2 | ft-08 mvp
Story | US-013 | EP-03 | Story | Today and Inbox screens with swipe actions | P0 | 5 | Wave 2 | WS-A | 2 | ft-08 mvp
Story | US-014 | EP-03 | Story | Task detail screen with notes and subtasks | P0 | 3 | Wave 2 | WS-A | 2 | ft-08 mvp
Story | US-015 | EP-05 | Story | Quick-add with AI parse preview | P0 | 5 | Wave 3 | WS-A | 2 | ft-15 mvp
Story | US-016 | EP-05 | Story | Natural-language parser: dates, priority, timezone | P0 | 3 | Wave 3 | WS-C | 2 | ft-15 mvp
Story | US-017 | EP-06 | Story | AI task breakdown into subtasks with estimates | P1 | 5 | Wave 3 | WS-A | 2 | ft-17 mvp
Story | US-018 | EP-02 | Story | Settings screen shell and preference registry | P1 | 2 | Wave 3 | WS-A | 2 | ft-49 phase-2
Story | US-019 | EP-07 | Story | Work hours and daily capacity settings | P1 | 3 | Wave 3 | WS-A | 3 | ft-18 phase-2
Story | US-020 | EP-07 | Story | AI daily plan generation | P1 | 8 | Wave 3 | WS-C | 3 | ft-19 phase-2
Story | US-021 | EP-07 | Story | Daily plan view with reorder and accept | P1 | 5 | Wave 3 | WS-A | 3 | ft-20 phase-2
Story | US-022 | EP-05 | Story | Edit and undo AI-created tasks | P1 | 2 | Wave 3 | WS-A | 3 | ft-16 phase-2
Story | US-023 | EP-14 | Story | Crash reporting with Sentry and source maps | P1 | 2 | Wave 3 | WS-D | 3 | ft-43 phase-2
Story | US-024 | EP-13 | Story | TestFlight and Play beta builds with OTA updates | P1 | 3 | Wave 3 | WS-D | 3 | ft-39 phase-2
Story | US-025 | EP-14 | Story | AI eval harness with golden sets and CI gate | P1 | 5 | Wave 3 | WS-E | 3 | ft-45 phase-2
Story | US-026 | EP-08 | Story | Local due-date reminders | P1 | 3 | Wave 4 | WS-A | 4 | ft-21 phase-2
Story | US-027 | EP-08 | Story | Notification permission flow and quiet hours | P1 | 3 | Wave 4 | WS-A | 4 | ft-21 phase-2
Story | US-028 | EP-07 | Story | Re-plan on missed or finished tasks | P1 | 3 | Wave 4 | WS-C | 4 | ft-20 phase-2
Story | US-029 | EP-03 | Story | Offline-first sync across devices | P1 | 8 | Wave 4 | WS-B | 4 | ft-11 phase-2
Story | US-030 | EP-03 | Story | Lists, tags and filters | P2 | 5 | Wave 4 | WS-A | 4 | ft-09 phase-2
Story | US-031 | EP-03 | Story | Recurring tasks (RRULE) | P2 | 5 | Wave 4 | WS-A | 4 | ft-10 phase-2
Story | US-032 | EP-08 | Story | Push token registration and server sender | P1 | 5 | Wave 4 | WS-C | 5 | ft-22 phase-2
Story | US-033 | EP-08 | Story | Buddy check-ins with quick-reply actions | P1 | 5 | Wave 4 | WS-C | 5 | ft-23 phase-2
Story | US-034 | EP-09 | Story | Detect repeatedly postponed tasks | P2 | 3 | Wave 4 | WS-A | 5 | ft-24 phase-2
Story | US-035 | EP-09 | Story | AI 10-minute starter step | P2 | 3 | Wave 4 | WS-C | 5 | ft-24 phase-2
Story | US-036 | EP-02 | Story | Sign in with Apple and Google | P2 | 3 | Wave 4 | WS-B | 5 | ft-05 phase-2
Story | US-037 | EP-13 | Story | Onboarding flow (hours, quiet hours, tone) | P1 | 5 | Wave 4 | WS-A | 5 | ft-38 phase-2
Story | US-038 | EP-14 | Story | Maestro E2E flows for critical paths | P1 | 5 | Wave 4 | WS-E | 5 | ft-44 phase-2
Story | US-039 | EP-13 | Story | Data export and account deletion | P0 | 5 | Wave 4 | WS-B | 6 | ft-37 phase-2
Story | US-040 | EP-13 | Story | Privacy policy, terms and AI disclosure | P0 | 2 | Wave 4 | WS-D | 6 | ft-37 phase-2
Story | US-041 | EP-09 | Story | Buddy chat with confirmed actions | P1 | 8 | Wave 5 | WS-C | 6 | ft-25 phase-2
Story | US-042 | EP-09 | Story | Buddy tone and language (English/Taglish) | P3 | 3 | Wave 5 | WS-C | 6 | ft-26 phase-2
Story | US-043 | EP-10 | Story | Voice capture via speech recognition | P1 | 5 | Wave 5 | WS-A | 6 | ft-27 phase-2
Story | US-044 | EP-10 | Story | Photo-to-tasks (vision extraction) | P2 | 5 | Wave 5 | WS-A | 6 | ft-28 phase-2
Story | US-045 | EP-10 | Story | Media upload limits, consent and auto-deletion | P1 | 3 | Wave 5 | WS-C | 7 | ft-29 phase-2
Story | US-046 | EP-11 | Story | Weekly completion statistics | P2 | 3 | Wave 5 | WS-B | 7 | ft-30 phase-2
Story | US-047 | EP-11 | Story | AI weekly review and suggestion | P2 | 5 | Wave 5 | WS-C | 7 | ft-31 phase-2
Story | US-048 | EP-14 | Story | Accessibility: labels, dynamic type, touch targets | P1 | 3 | Wave 5 | WS-E | 7 | ft-46 phase-2
Story | US-049 | EP-14 | Story | Performance budgets for startup and lists | P2 | 3 | Wave 5 | WS-E | 7 | ft-48 phase-2
Story | US-050 | EP-13 | Story | v1.0 App Store and Google Play submission | P0 | 5 | Wave 5 | WS-D | 7 | ft-39 phase-2
Story | US-051 | EP-14 | Story | Consent-gated product analytics | P2 | 3 | Wave 5 | WS-D | 7 | ft-47 phase-2
Story | US-052 | EP-14 | Story | Filipino and English UI localization | P3 | 3 | Wave 5 | WS-A | 7 | ft-46 phase-2
Story | US-053 | EP-03 | Story | Full-text task search (FTS5) | P2 | 3 | Wave 6 | WS-B | 8 | ft-09 phase-3
Story | US-054 | EP-12 | Story | Shared spaces: membership, roles, RLS | P1 | 5 | Wave 6 | WS-B | 8 | ft-32 phase-3
Story | US-055 | EP-12 | Story | Agent scopes and confirmations (server-enforced) | P1 | 5 | Wave 6 | WS-C | 8 | ft-35 phase-3
Story | US-056 | EP-12 | Story | Space invites by link or code | P1 | 5 | Wave 6 | WS-B | 8 | ft-32 phase-3
Story | US-057 | EP-12 | Story | Realtime shared lists | P1 | 8 | Wave 6 | WS-B | 8 | ft-33 phase-3
Story | US-058 | EP-12 | Story | Task assignment and comments | P2 | 5 | Wave 6 | WS-A | 9 | ft-33 phase-3
Story | US-059 | EP-12 | Story | Space notifications and muting | P2 | 3 | Wave 6 | WS-C | 9 | ft-33 phase-3
Story | US-060 | EP-12 | Story | Shared AI agent via @buddy in spaces | P1 | 8 | Wave 6 | WS-C | 9 | ft-34 phase-3
Story | US-061 | EP-12 | Story | Agent action audit log | P1 | 3 | Wave 6 | WS-B | 9 | ft-35 phase-3
Story | US-062 | EP-12 | Story | AI workload-balancing proposals | P2 | 5 | Wave 6 | WS-C | 9 | ft-34 phase-3
Story | US-063 | EP-13 | Story | Pro subscription via RevenueCat | P2 | 8 | Wave 6 | WS-B | 10 | ft-36 phase-3
Story | US-064 | EP-13 | Story | Tier-based AI quotas | P2 | 3 | Wave 6 | WS-C | 10 | ft-36 phase-3
Story | US-065 | EP-13 | Story | Calendar-aware planning (busy times only) | P3 | 5 | Wave 6 | WS-A | 10 | ft-40 phase-3
Story | US-066 | EP-13 | Story | Home-screen Today widget | P3 | 5 | Wave 6 | WS-A | 10 | ft-41 phase-3
Story | US-067 | EP-04 | Story | Experimental on-device parsing | P3 | 8 | Wave 6 | WS-C | 10 | ft-42 phase-3
Task | TT-01 | US-001 | Task | Create GitHub repo, protect main, require CI + 1 review | P0 |  | Wave 1 | WS-D | 1 | infra
Task | TT-02 | US-005 | Task | Provision Supabase dev/staging/prod projects and EAS env | P0 |  | Wave 1 | WS-B | 1 | infra
Task | TT-03 | US-002 | Task | Create EAS project, credentials and build profiles (development/preview/production) | P0 |  | Wave 1 | WS-D | 1 | infra
Task | TT-04 | US-007 | Task | Drizzle SQLite schema v1 and migration runner | P0 |  | Wave 1 | WS-B | 1 | db
Task | TT-05 | US-005 | Task | Postgres schema v1 migrations plus RLS policies for profiles | P0 |  | Wave 1 | WS-B | 1 | db
Task | TT-06 | US-029 | Task | Add sync columns and triggers (updated_at, deleted_at, server_seq) | P1 |  | Wave 4 | WS-B | 4 | db
Task | TT-07 | US-033 | Task | pg_cron + pg_net schedule for check-ins and token cleanup | P1 |  | Wave 4 | WS-C | 5 | db
Task | TT-08 | US-054 | Task | Spaces, members, comments, agent_actions tables with RLS | P1 |  | Wave 6 | WS-B | 8 | db
Task | TT-09 | US-008 | Task | Edge Function ai-gateway router and provider interface | P0 |  | Wave 2 | WS-C | 1 | api
Task | TT-10 | US-010 | Task | Shared Zod schema package used by app and functions | P0 |  | Wave 2 | WS-C | 1 | api
Task | TT-11 | US-029 | Task | sync_pull and sync_push RPCs with conflict rules | P1 |  | Wave 4 | WS-B | 4 | api
Task | TT-12 | US-063 | Task | revenuecat-webhook function and subscription table | P2 |  | Wave 6 | WS-B | 10 | api
Task | TT-13 | US-003 | Task | NativeWind theme and tokens, dark mode | P0 |  | Wave 1 | WS-A | 1 | fe
Task | TT-14 | US-012 | Task | Task repository hooks with TanStack Query and optimistic updates | P0 |  | Wave 2 | WS-A | 2 | fe
Task | TT-15 | US-022 | Task | Undo store and toast component | P1 |  | Wave 3 | WS-A | 3 | fe
Task | TT-16 | US-033 | Task | Notification categories with quick-reply actions | P1 |  | Wave 4 | WS-C | 5 | fe
Task | TT-17 | US-010 | Task | Versioned prompt templates in repo with eval hooks | P0 |  | Wave 2 | WS-C | 1 | be
Task | TT-18 | US-009 | Task | Usage ledger table and quota check function | P0 |  | Wave 2 | WS-C | 1 | be
Task | TT-19 | US-008 | Task | Per-route model routing config (cheap model for parse, stronger for plan/review) | P0 |  | Wave 2 | WS-C | 1 | be
Task | TT-20 | US-005 | Task | RLS automated test suite (pgTAP or SQL tests) | P0 |  | Wave 1 | WS-B | 1 | security
Task | TT-21 | US-008 | Task | Secrets management and key rotation runbook | P0 |  | Wave 2 | WS-C | 1 | security
Task | TT-22 | US-011 | Task | Prompt-injection test corpus (20+ cases) in CI | P0 |  | Wave 2 | WS-C | 2 | security
Task | TT-23 | US-055 | Task | Agent scope enforcement middleware in gateway | P1 |  | Wave 6 | WS-C | 8 | security
Task | TT-24 | US-002 | Task | GitHub Actions: lint, typecheck, unit, eval, E2E workflows | P0 |  | Wave 1 | WS-D | 1 | devops
Task | TT-25 | US-024 | Task | EAS Update channels per environment and rollback procedure | P1 |  | Wave 3 | WS-D | 3 | devops
Task | TT-26 | US-005 | Task | Supabase CLI migration pipeline from PR to staging to prod | P0 |  | Wave 1 | WS-B | 1 | devops
Task | TT-27 | US-023 | Task | Sentry init, source map upload, PII scrubbing | P1 |  | Wave 3 | WS-D | 3 | monitoring
Task | TT-28 | US-051 | Task | PostHog event taxonomy and consent gate | P2 |  | Wave 5 | WS-D | 7 | monitoring
Task | TT-29 | US-009 | Task | AI cost dashboard (SQL view) with daily spend alert | P0 |  | Wave 2 | WS-C | 1 | monitoring

## Agile & AI Practices
Practice | Detail
Definition of Ready | AC written and testable; prerequisites done; sized at 8 points or less (split if larger); API contract or screen linked; security/privacy/AI-cost implications noted.
Definition of Done | AC met and demoed; reviewed PR merged with CI green; unit + integration pass (E2E on critical paths); RLS/security tests pass where relevant; AI eval baseline not regressed; no new Sentry errors; docs/tickets note updated; migrations reversible.
Cadence (solo) | Monday: sprint planning (30 pts). Daily: 10-minute self standup. Friday: demo on device + retro + backlog refinement for next sprint.
AI-assisted development | Use coding agents per story: spec from the ticket AC > plan > implement in a branch > run tests > self-review diff > PR. Always attach the ticket doc in docs/tickets/TB-###.md.
Agent model routing | Simple questions and lookups: Sonnet-class. Feature development: Opus-class. Hard or critical work (sync conflict rules, RLS policies, agent scope enforcement, gateway security): top-tier model with a second review pass.
AI-assisted testing | Agents draft unit tests and Maestro flows from AC; human reviews. AI evals (golden sets) gate prompt and model changes in CI.
AI-assisted docs and review | Agents update docs/tickets notes and propose PR summaries; run a code-review pass for security, performance and correctness before human review.
Reuse-first | Before creating a component, hook or utility, check for an existing shared one or pattern; standardize repeated solutions instead of duplicating.
Documentation discipline | CLAUDE.md is updated only when an epic completes or a decision becomes stable and reusable; per-ticket detail lives in docs/tickets/TB-###.md.
Estimation | Fibonacci points; recalibrate velocity after Sprint 2 and re-run the sprint plan.

## Gaps & Assumptions
Topic | Gap / assumption | Impact | Recommendation | Status
Team size and velocity | Assumed solo developer with AI coding agents, 1-week sprints, 30 points per sprint | Sprint dates and MVP-in-2-weeks hinge on this | Confirm; re-run scheduling if velocity differs | Assumption
Sprint 1 start date | Assumed Monday 2026-11-02 | All sprint dates shift | Confirm real start date | Assumption
Target platforms | iOS and Android both in v1.0 | Store work doubles; widgets differ by OS | Confirm; if iOS-first, move Android items out of Wave 5 | Assumption
AI provider and data policy | Claude via gateway; text, audio transcripts and images may be sent to the provider | Drives privacy policy and consent copy | Review provider data-retention terms before beta | Open
Pricing and quotas | Free limits (30 AI calls/hour, daily token cap) and Pro tier price are placeholders | Affects cost model and billing story | Decide after 4 weeks of ledger data | Open
Taglish and Filipino support | Parser and chat expected to handle Taglish; speech recognition locale support unverified per device | Voice accuracy risk | Test fil-PH on target devices in Sprint 6 | Open
Expo SDK version | SDK 56 verified stable (May 2026); SDK 57 listed Jun 2026 on expo.dev/sdk | Library compatibility | Use the latest stable SDK at scaffold time and record it in CLAUDE.md | Open
expo-speech-recognition maintenance | Community library; compatibility table last dated July 2025 | Voice story could slip | Check release status in Sprint 5 before building; fallback is cloud STT | Open
Android widgets | Expo Widgets stability confirmed for iOS only | Widget story scope | Ship iOS widget first; decide Android approach in Phase 3 | Open
NFR targets | Targets assumed: crash-free 99.5%, cold start <2.5s, AI p95 <6s, RTO 4h, RPO 15 min | Test and monitoring thresholds | Confirm or adjust | Assumption
Data retention | Soft-deleted rows purge after 30 days; agent logs 90 days; raw media 24 hours | Compliance and storage | Confirm with privacy policy | Assumption
Age and consent | Adult users assumed; no child-directed features | Store age rating and privacy rules | Confirm audience | Assumption
Spaces business model | Spaces assumed Pro-only at launch | Billing dependency order | Confirm before Sprint 8 | Open
Jira import behavior | Field mapping for Sprint, Labels and issue links depends on Jira project type | Import may need manual mapping | Test with 3 rows first (see import guide) | Open
Holiday period | Sprints 8-9 fall on 2026-12-21 to 2027-01-01, overlapping Christmas and New Year | Spaces work may slip | Plan lighter capacity or shift Phase 3 start | Assumption